## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-11-18 | Done | Block preapration | Intro Block lecture | Lecture | ILO 8.6 | 1 | 1.5 | 0.5 |  | The lecture was 30 minutes more
2024-11-18 | Done |  | Lunch | Lunch | - | 1 | 1 | 0
2024-11-18 | Done | Data lab task | Installing fiji | Study | ILO 6.4 | 0.5 | 0.5 | 0 |  | Installed Fiji and watched the video how to use labkit
2024-11-18 | Done | Future activity | Pre master lecture (avaiancity) | Lecture | ILO 2.6 | 1.5 | 1.5 | 0
2024-11-18 | Done | Data lab task | Marking the first image | Study | ILO 6.4 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/tree/46c3d6f221287b9d300e5dc9549111335a308e65/datasets/ready_5_images
2024-11-19 | Done | Data lab task | Masking the second image | Study | ILO 6.4 | 1 | 3 | 2 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/tree/46c3d6f221287b9d300e5dc9549111335a308e65/datasets/ready_5_images | I did not install the correct assignment of how to actually label them
2024-11-19 | Done | Data lab task | Masking the third image | Study | ILO 6.4 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/tree/46c3d6f221287b9d300e5dc9549111335a308e65/datasets/ready_5_images
2024-11-19 | Done | Data lab task | Masking the forth one | Study | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/tree/46c3d6f221287b9d300e5dc9549111335a308e65/datasets/ready_5_images
2024-11-19 | Done | Data lab task | Masking the fifth one | Study | ILO 6.4 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/tree/46c3d6f221287b9d300e5dc9549111335a308e65/datasets/ready_5_images
2024-11-20 | Done | Data lab task | Metting with a client | Study | ILO 6.4 | 1.5 | 2.5 | 1 |  | We were adrressing on how each individual should go color the roots and sthe shoots
2024-11-20 | Done | Evidencing | Worklog | Evidencing | ILO 1.6 | 1 | 1 | 0
2024-11-20 | Done | Self_study | First notebook for basics (part) | Study | ILO 1.6 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/46c3d6f221287b9d300e5dc9549111335a308e65/self_stduy/2024-25-Y2-BlockB-main/2024-25-Y2-BlockB-main/self_study/w1/1.%20Basics.ipynb
2024-11-21 | Done | Self_study | First notebook for basics | Study | ILO 6.4 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/46c3d6f221287b9d300e5dc9549111335a308e65/self_stduy/2024-25-Y2-BlockB-main/2024-25-Y2-BlockB-main/self_study/w1/1.%20Basics.ipynb
2024-11-21 | Done | Self_study | Thresholding and Filtering | Study | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/46c3d6f221287b9d300e5dc9549111335a308e65/self_stduy/2024-25-Y2-BlockB-main/2024-25-Y2-BlockB-main/self_study/w1/2.%20Thresholding%20and%20Filtering.ipynb
2024-11-22 | Cancelled | Self_study | Morphological Operation | Study | ILO 6.4 | 3 |  | -3
2024-11-23 | Done | Evidencing | Learning log | Evidencing | ILO 1.6 | 1 | 1 | 0
2024-11-23 | Done | self development | Pdocast from footbal analytics departament form Arsenal | Study | ILO 2.6 | 1.5 | 1.5 | 0 |  | The podcast fuess was Sarah Rudd she is a Data Scientist in Arsenal FC
2024-11-23 | Done | Evidencing | Worklog | Evidencing | ILO 1.6 | 0.5 | 0.5 | 0
0
|  |  |  | Total Hours |  | 27.5 | 28 | 0.5
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2024-11-26 | Done | Data lab | Stand up | Study | ILO 1.6 | 0.25 | 0.25 | 0
2024-11-26 | Done | Data lab Task 1 | Finnalising with labelling images | Study | ILO 6.4 | 2 | 2 | 0
2024-11-26 | Done | Self stduy | Morphological Operation | Study | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/46c3d6f221287b9d300e5dc9549111335a308e65/self_stduy/2024-25-Y2-BlockB-main/2024-25-Y2-BlockB-main/self_study/w1/3.%20Morphological%20Operations.ipynb
2024-11-27 | Done | Self study | Morphological Operation | Study | ILO 6.4 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/46c3d6f221287b9d300e5dc9549111335a308e65/self_stduy/2024-25-Y2-BlockB-main/2024-25-Y2-BlockB-main/self_study/w1/3.%20Morphological%20Operations.ipynb
2024-11-27 | Done | Self study | Edge and Contour detection | Study | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/46c3d6f221287b9d300e5dc9549111335a308e65/self_stduy/2024-25-Y2-BlockB-main/2024-25-Y2-BlockB-main/self_study/w1/4.%20Edge%20and%20Contour%20detection.ipynb
2024-11-27 | Done | Data lab task | Peer review | Study | ILO 2.6 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/042f0c3fb8f6d09fda590fa46501f2862e00f554/Peer_review_Niels/peer_review_Niels.pdf
2024-11-27 | Done | Self stduy | Image Segmentation | Study | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/46c3d6f221287b9d300e5dc9549111335a308e65/self_stduy/2024-25-Y2-BlockB-main/2024-25-Y2-BlockB-main/self_study/w1/5.%20Image%20Segmentation.ipynb
2024-11-28 | Done | Data lab | Stand up | Meeting | ILO 1.6 | 0.25 | 0.25 | 0
2024-11-28 | Done | Data lab | Peer review Finishing | Study | ILO 2.6 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/042f0c3fb8f6d09fda590fa46501f2862e00f554/Peer_review_Niels/peer_review_Niels.pdf
2024-11-28 | Done | Task 2 | Making a function to go through each file | Study | ILO 2.6 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/042f0c3fb8f6d09fda590fa46501f2862e00f554/datalab_tasks/task2/task_2.ipynb
2024-11-28 | Done | Evidence | Worklog | Evidencing | ILO 1.6 | 1 | 1 | 0
2024-11-29 | Done | Task 2 | Edge detection | Study | ILO 6.4 | 3 | 3 | 0 |  | I cropped one of the images to the exat way but now I nee to adapt so it actually detect each of the pixels
2024-11-29 | Done | Task 2 | Crop detection | Study | ILO 6.4 | 2 | 2 | 0
2024-11-30 | Done | Task 15 | Npec client research | Study | ILO 2.6 | 1 | 1 | 0
0
|  |  |  | Total Hours |  | 26.5 | 26.5 | 0
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-12-02 | Done | datalab | Feedback sesion | Study | ILO 1.6 | 1 | 1 | 0
2024-12-02 | Done | datalab | Segmantation mask 2 | Study | ILO 1.6 | 4 | 4 | 0
2024-12-02 | Done | datalab | Meeting for a Exchange student prgrammes meeting | Study |  | 2 | 2 | 0
2024-12-03 | Done | Notebook 6 | Object detection | Study | ILO 6.4 | 2 | 2 | 0
2024-12-03 | Done | Task 2 | Task 2 adjustment | Study | ILO 6.4 | 3 | 3 | 0 |  | My code said is working but still I need to do some adjustment
2024-12-03 | Done | Task 1 | Peer review me mask 2 | Study | ILO 6.4 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/2824f0b7e14ddc54cad4c0681faac7f6067e203c/Peer_review_me/232725_feedback.docx
2024-12-04 | Done | Task 2 | Task 2 done | Study | ILO 6.4 | 3 | 3 | 0
2024-12-04 | Done | Task 3 | Task 3 starting | Study | ILO 6.4 | 2 | 2 | 0
2024-12-04 | Done | Evidencing | Learning Log | Evidencing | ILO 1.6 | 1 | 2 | 1
2024-12-05 | Done | Task 3 | Task 3 applying morphlogical operations | Study | ILO 5.1 | 1 | 1 | 0
2024-12-05 | Done
2024-12-06 | Done
2024-12-06 | Done
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 21 | 22 | 1
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-12-09 | Done | Task 3 | Talking with a colleague how to reslove the issue I had | Study | ILO 6.4 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/2824f0b7e14ddc54cad4c0681faac7f6067e203c/datalab_tasks/task3/task_3_test.ipynb
2024-12-09 | Done | Task 3 | Continue changing the code | Study | ILO 2.6 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/2824f0b7e14ddc54cad4c0681faac7f6067e203c/datalab_tasks/task3/task_3_test.ipynb
2024-12-09 | Done | Task 3 | Continue changing the code | Study | ILO 2.6 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/2824f0b7e14ddc54cad4c0681faac7f6067e203c/datalab_tasks/task3/task_3_test.ipynb
2024-12-09 | Done | Evidencing | Evidencing | Study | ILO 1.6 | 1 | 1 | 0
2024-12-10 | Done | Task 4 | Finding matching images | Study | ILO 2.6 | 2.5 | 2.5 | 0 |  | For this task I used the 2023 dataset to find the corresponding name and mask
2024-12-10 | Done | Task 4 | making a script to search the corresponding masks | Study | ILO 1.6 | 2 | 2 | 0 |  | For the 2023 dataset only a few had root mask path so I needed to make a script to see the mask have it then find the corresponding image
2024-12-10 | Done | task 4 | Cropping images | Study | ILO 6.4 | 3 | 3 | 0
2024-12-10 | Done | Task 4 | Patching first phase | Study | ILO 2.6 | 3 | 3 | 0 |  | I did patching but it is not done yet there is still more to improve
2024-12-11 | Done | Task 4 | Rearraging the folder | Programming | ILO 2.6 | 2 | 2 | 0 |  | I wanted to ensure that all of the corresponding mask and images are taken since 3, 4 were missing
2024-12-11 | Done | Task 4 | Adding the 2024 dataset | Programming | ILO 2.6 | 2 | 2 | 0 |  | I had some problem my code that worked for extracting the 2023 dataset did not work
2024-12-11 | Done | Task 4 | Making a notebook for extracting validation dataset | Programming | ILO 6.4 | 2 | 2 | 0 |  | Do not have the the link for how preprocess everything so my github desktop stays empty
2024-12-12 | Done | Task 4 | Notebook 7 | Programming | ILO 6.4 | 2 | 2
2024-12-12 | Done | Task4 | Making the code for the train dataset | Programming | ILO 6.4 | 3 | 3
2024-12-13 | Done | Task4 | [5 empty] | 0
0
|  |  |  | Total Hours |  | 30.5 | 30.5 | 0
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | I was flying to my home country during this week so I made a new Holiday sector so I can put all of the important stuff in there
2024-12-16 | Done | Task 4 | Redoing the whole patchifying function for 2023 dataset | Programming | ILO 6.4 | 3 | 3 | 0 |  | I made it work at the end when I made a list to look at the first 53
2024-12-16 | Done | Task 4 | Managing all the data with 2024 dataset | Programming | ILO 6.4 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/da885f5ada0b03a02848b536a240e73bfa560f91/datalab_tasks/task5/task_4_for_train_24.ipynb | spllited all of the datasets correctly
2024-12-16 | Done | Task 4 | Make a function to separate 2024 | Programming | ILO 2.6 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/da885f5ada0b03a02848b536a240e73bfa560f91/datalab_tasks/task5/task_4_for_train_24.ipynb | Made a notebook to get all of the train dataset in one placed all of the cropped images
2024-12-17 | Done | Task 5 | Making the tempalte for making the mode | Programming | ILO 6.4 | 3 | 3 | 0
2024-12-17 | Done | Task 4 | Fixing the pacifying for the 2024 validation set | Programming | ILO 6.4 | 4 | 4 | 0
2024-12-17 | Done | Evidence | Working log | Evidencing | ILO 1.6 | 1 | 1 | 0
2024-12-18 | Done | Task 5 | Installing a new environment | Study | ILO 6.4 | 2 | 2 | 0 |  | made a new environment because I didn't install the tenserflow as It should have been
2025-12-18 | Done | Task 5 | Installing the new drivers on my computer from Nvidia | Study | ILO 6.4 | 2 | 2 | 0
2024-12-19 | Done | Task 4 | cropping the images | Programming | ILO 2.6 | 2 | 2 | 0 |  | My image didn't work for the 2024 dataset so I made a new one
2024-12-19 | Done | Task 4 | Task 4 | Programming | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/da885f5ada0b03a02848b536a240e73bfa560f91/datalab_tasks/task5/task_4_for_val_24.ipynb | saw the requirement of only the val starting images in one to be the validation dataset
2024-12-19 | Done | Task 4
2024-12-20 | Done | Max 4 hours tasks | Flying |  |  | 6 | 6 | 0
| Done | Max 4 hours tasks | [5 empty] | 0
| Done | Max 4 hours tasks | [5 empty] | 0
| Done | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 31 | 31 | 0
HOLIDAY
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | This is extra added
2024-12-21 | Done | Task 4 | Trying to run task 5 again | Programming | ILO 6.4 | 1 | 1 | 0 |  | It did not work and understood my models mask were not good enough
2025-12-22 | Done | Task 4 | Redid my entire patching function | Programming | ILO 6.4 | 2 | 2 | 0
2025-12-25 | Done | task 5 | training a model | Programming | ILO 6.4 | 4 | 4 | 0 |  | still got 0
2024-12-19 | Done | task 4 | checker for right image data generator | Programming | ILO 6.4 | 2 | 2 | 0 |  | my friend helped me make a function that checks through the images to see what is wrong with them
2024-12-20 | Done | Max 4 hours tasks |  | Programming | ILO 6.4 | 1 | 1 | 0
2024-12-21 | Done | Max 4 hours tasks |  | Programming | ILO 6.4 | 2 |  | 2
2024-12-22 | Done | Max 4 hours tasks |  | Programming | ILO 6.4 | 4 |  | 4
|  |  |  | Total Hours |  | 16 | 10 | -6
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-06 | Done | Task 5 | Training the model | Programming | ILO 6.4 | 2 | 2 | 0 |  | I got f1 score of 70
2025-01-06 | Done | Task 5 | Inference on the model | Programming | ILO 6.4 | 1.5 | 1.5 | 0 |  | It did not work accordingly my image output was really bad that is why I ma re training the model
2025-01-06 | Done | Evidence | Working, Learning Log | Evidencing | ILO 6.4 | 2 | 2 | 0
2025-01-06 | Done | task 5 | Training the model once again | Waiting | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/ac7eca7107680388afed589c7b1c24140b9120f5/datalab_tasks/task5/Training_model_1.ipynb | I got f1 score of 80 in the second iteration
2025-01-06 | Done | Task5 | Inference on the model | Waiting | ILO 6.4 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/ac7eca7107680388afed589c7b1c24140b9120f5/datalab_tasks/task5/Training_model_1.ipynb | It worked this time my model completed all of the steps and it worked
2025-01-07 | Done | Task 5 | Inference code | Programming | ILO 6.4 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/ac7eca7107680388afed589c7b1c24140b9120f5/datalab_tasks/task5/task5_inference_template%20-%20Copy1.ipynb | Doing the inference model again
7/125 | Done | Task 5 | Reviewng my mask with my colleagues | Programming | ILO 2.6 | 3 | 3 | 0 |  | Late I found out that I was just overfitting
2025-01-07 | Done | Task 5 | Fixing the inference code | Programming | ILO 2.6 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/ac7eca7107680388afed589c7b1c24140b9120f5/datalab_tasks/task5/task5_inference_template%20-%20Copy1.ipynb | I fixed the code and got a better more workable image
2025-01-08 | Done | Task 5 | Training model 2 | Waiting | ILO 2.6 | 2 | 2 | 0 |  | I tried to make a model with step size on my locl machinhe but it took way longer than expected
2025-01-08 | Done | Task 6 | Using morphological operations | Programming | ILO 6.4 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/ac7eca7107680388afed589c7b1c24140b9120f5/datalab_tasks/Pipeline/Pipeline_Task_6_7.ipynb | using morphological operations on the test image
2025-01-08 | Done | Task 7 | Skeletonize | Programming | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/ac7eca7107680388afed589c7b1c24140b9120f5/datalab_tasks/Pipeline/Pipeline_Task_6_7.ipynb
2025-01-08 | Done | Task 7 | Logic for the sumarrization of the brach tope data | Programming | ILO 6.4 | 2 | 2 | 0 |  | making the logic to take the lowest point of an id skelton and the top one
2025-01-08 | Done | Task 8 | Preparing the Pipeline | Programming | ILO 6.4 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/e8b2c2da8919e62c23c3e758436921afb0e75fc4/datalab_tasks/Task8/task_8.ipynb | Starting the pipeline for task 8
2025-01-09 | Done | Task 8 | Finishing the pipeline | Programming | ILO 6.4 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/e8b2c2da8919e62c23c3e758436921afb0e75fc4/datalab_tasks/Task8/task_8.ipynb | Finished the pipeline for task 8
2025-01-09 | Done | Task 8 | Metting with a client | Meeting | ILO 1.6 | 1 | 1 | 0 |  | I got a meeting to do a
2025-01-09 | Done | Task 8 | Giving a submission to kaggle | Programming | ILO 6.4 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/e8b2c2da8919e62c23c3e758436921afb0e75fc4/datalab_tasks/Task8/submission.csv | this got a score of 93
2025-01-09 | Done | Task 8 | Adjusting a logic to have a better score | Programming | ILO 6.4 | 3 | 3 | 0 |  | the logic is to sepearte the
2025-01-09 | Done | Task 8 | Making a submission to kaggle with the new logic | Programming | ILO 6.4 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/63f393df72b4caafffc6160269db7a3bcde59402/datalab_tasks/Task8/task_8%20_12-01.ipynb | the logic was to make the whole picture to have a maximum of 5 roots that are the biggest in each sector
2025-01-09 | Done | Task 8 | Making more logic for an even better score | Programming | ILO 6.4 | 1 | 1 | 0 |  | The top node is always in the above 50 % so to remove every noise that is bellow the 50 % with logic I desriped in the cell above
2025-01-09 | Blocked | Task 5 | Making another model | Waiting | ILO 6.4 | 3 | 3 | 0 |  | this model is with more step size to see if it is actually going to improve the model more, but waited 3 hours and it was only on 2 epochs
2025-01-10 | Done | Task 8 | Fixing the logic for the submission | Programming | ILO 6.4 | 1 | 1 | 0 |  | got my best score so far of 4 and got 5th place on the kaggle competion
2025-01-10 | Done | Task 10,11 | Metting with a Niels | Meeting | ILO 8.6 | 1 | 1 | 0 |  | We talked about the hyperparameters since I have not done them we are going to use his already built gymnasium so we know what are the best parameters
2025-01-10 | Done | Task 9 | Understanding the Task | Programming | ILO 8.6 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/63f393df72b4caafffc6160269db7a3bcde59402/datalab_tasks/Task8/task_8%20_12-01.ipynb
2025-01-10 | Done | Task 9 | trying to finalize Task 9 | Programming | ILO 8.6 | 1 | 1 | 0
2025-01-10 | Done | Task 8 | Improving the Morphological operations | Programming | ILO 6.4 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/63f393df72b4caafffc61602 69db7a3bcde59402/datalab_tasks/Task8/task_8%20_12-01.ipynb | Made more morphological components iterating throug closing and aslo made preprocessing after for a better quality masks
2025-01-10 | Done | Evidence | Working log | Evidencing | ILO 1.6 | 1 | 1 | 0
2025-01-11 | Done | Task 5 | Training another model | Waiting | ILO 2.6 | 8 | 8 | 0 |  | I changed the step size of the patchfying to 128
2025-01-11 | Done | Task 8 | Kaagle submission | Study | ILO 8.6 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/63f393df72b4caafffc6160269db7a3bcde59402/datalab_tasks/Task8/Final_submission_1.csv | I got a lower score of 3.7786
2025-01-11 | Done | Task 5 | Made new made an architecture | Study | ILO 6.4 | 3 | 3 | 0
|  |  |  | Total Hours |  | 60.5 | 60.5 | 0
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-13 | Done | Task 9 | Making the controlller work smoothly | Programming | ILO 8.8 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/63f393df72b4caafffc6160269db7a3bcde59402/datalab_tasks/task9-10-11/Simulation.py | I used 0.9 for all the spped and step size to about 130
2025-01-13 | Done | Task 10 | Wrapper and making all the dependencies | Programming | ILO 8.7 | 2 | 2 | 0
2025-01-13 | Done | Task 11,13,10 | Video of dean explaining the wrapper | Study | ILO 2.6 | 1 | 1 | 0 |  | It explained a lot what actually the whole RL process looks like
2025-01-14 | Done | Task 11 | Task 11 RL | Programming | ILO 8.7 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/63f393df72b4caafffc6160269db7a3bcde59402/datalab_tasks/task9-10-11/Task11.py | Try to run the Rl did not work
2025-01-14 | Done | Task 11 | Task 11 RL | Programming | ILO 8.7 | 2 | 2 | 0 |  | I made the Reinforcment learning work
2025-01-14 | Done | Evidence | Working log | Study | ILO 1.6 | 1 | 1 | 0
2025-01-14 | Done | Task 10 | Wrapper and still working | Programming | ILO 8.7 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/da885f5ada0b03a02848b536a240e73bfa560f91/datalab_tasks/task9-10-11/ot2_gym_wrapper.py | My wrapper and reviewed it back
2025-01-14 | Done | Evidencing | Learning log | Evidencing | ILO 1.6 | 3 | 3 | 0 |  | I cathed up on Learning log from week 3
2025-01-15 | Done | Task 10 | Task 10 wrapper changes | Programming | ILO 2.6 | 3 | 3 | 0 |  | I changed what is the end goal of the wrapper and I made it to be 0,001 cm
2025-01-15 | Done | Task 11 | Making a callback | Programming | ILO 2.6 | 1 | 1 | 0 |  | I mad a callback so it tracks the reward function if it goes up or not
2025-01-15 | Done | Helping | Adviced people | Study | ILO 1.6 | 2 | 2 | 0 |  | I helped people while my reinforcement learning was training because I do it locally
2025-01-15 | Done | Task 11 | Creating another trainer for task 11 | Programming | ILO 8.7 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/e2628a6e1453746d53152c9616b41e2b6771ef37/datalab_tasks/task9-10-11/Task_11.py | I also got a model waiting 4 hours for it to train completelly
2025-01-16 | Done | Evidencing | Working log | Evidencing | ILO 1.6 | 1 | 1 | 0 |  | Evidencing
2025-01-16 | Done | Task11 | Training models on the server and RL | Programming | ILO 8.7 | 1 | 1.2 | 0.2 |  | changed the learning rate right to 0,0001 to 0,00001
2025-01-16 | Done | Task11 | Training more models on the RL | Programming | ILO 8.7 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/e2628a6e1453746d53152c9616b41e2b6771ef37/datalab_tasks/task9-10-11/Task_11.py | Made more models with different parameters on 2 million steps
2025-01-16 | Done | Task12 | Strated doing the PID controller | Programming | ILO 8.6 | 2 | 2 | 0 |  | I made it work but my controller is still far away on the z axis
2025-01-17 | Done | Task12 | Continuing to make the pid controller | Testing | ILO 8.7 | 2 | 2 | 0 |  | My z axis was making to the top and didn't move, no matter where the z axis was
2025-01-17 | Done | Task12 | Finishing the PID controller | Programming | ILO 8.7 | 3 | 3 | 0 |  | Fixed made the whole PID Controller way easier
2025-01-17 | Done | Task12 | Testing the PID controller | Testing | ILO 8.8 | 2 | 2 | 0
2025-01-18 | Done | Task 8 | Adjusting a logic for sector 5 | Programming | ILO 2.6 | 3 | 3 | 0 |  | Mde a logic so it goes down the root that detect that is the biggest and makes a smaller box for sector 5
2025-01-18 | Done | Task 8 | Kaagle submission | Programming | ILO 2.6 | 2 | 2 | 0 |  | Got the same score on the Kaggle but I am sure that is the best model I can produce with the methods I used
2025-01-18 | Done | Task 11 | Testing the Rl to reach the desired goals | Testing | ILO 8.7 | 2 | 2 | 0
0
0
|  |  |  | Total Hours |  | 42 | 42.2 | 0.2
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-20 | Done | Task 8 | Kaagle submission | Waiting | ILO 8.6 | 3 | 3 | 0 |  | Watching with my colleagues the result from the, got 7th place on the kaggle public leaderboard
2025-01-20 | Done | Task 13 | Started with task 13 | Programming | ILO 8.6 | 2 | 2 | 0 |  | Made the evaluation to first make computer vision pipeline on a script and then make into combined script both and called the simualtion that I made
2025-01-20 | Done | Task 13 | Task 13 on notebook | Programming | ILO 8.6 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/83da535ef59f7023032785ef543240b734614f0c/datalab_tasks/task9-10-11/Pipeline_13_computer_vision.ipynb | Strate making a notebook for it, but it didn't work in the end
2025-01-21 | Done | Task 13 | Task 13 CV pipeline class | Programming | ILO 8.8 | 3.5 | 3.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/5d2e17c77770a2becb83f0dc63f2957cd0e3ea4f/datalab_tasks/task9-10-11/CV_pipeline.py | Made pipeline class so my PID Controller so my PID is way easier to use
2025-01-21 | Done | Task 13 | Task 13 PID Controller | Programming | ILO 8.8 | 2 | 3 | 1 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/5d2e17c77770a2becb83f0dc63f2957cd0e3ea4f/datalab_tasks/task9-10-11/Task_13_PID.py | Made the controller work finally
2025-01-21 | Done | Task 15 | Start with presentation | Design | ILO 1.6 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai2-adsai-PetarPaskalev232725/blob/5d2e17c77770a2becb83f0dc63f2957cd0e3ea4f/datalab_tasks/task15/Task15_presentation.pdf
2025-01-21 | Done | Task 13 | Task 13 with RL | Programming | ILO 8.8 | 2 | 2 | 0 |  | Tried to make the the RL work, but had some issues with the shape of the petri dish
2025-01-21 | Done | Task 15 | Finish presentation | Design | ILO 8.8 | 3 | 3 | 0
2025-01-22 | Done | Task 15 | Presenting | Presenting | ILO 8.8 | 0.5 | 0.5 | 0 |  | Got a feedback to do more error analysis from Jason, but overall really good
2025-01-22 | Done | Task 15 | Watching other presentations | Meeting | - | 5 | 5 | 0
2025-01-22 | Done |  | Drinks | Distraction | - | 2 | 4 | 2
2025-01-23 | Done | Evidencing | Working log | Evidencing | ILO 1.6 | 1 | 1 | 0
2025-01-23 | Done | Evidencing | Learning Log | Evidencing | ILO 1.6 | 2 | 2 | 0
2025-01-23 | Done | Max 4 hours tasks | Learning log evidencing | Evidencing | ILO 2.6 | 3 | 3 | 0
2025-01-23 | Done | Smart goal | Meeting with a client | Meeting | ILO 2.6 | 1 | 0.5 | -0.5 |  | Metting almost every week I attendted this meetings to help a client choose what they need to make an ai agent
2025-01-24 | Done | Evidence | continue evidencing | Evidencing | ILO 2.6 | 3 | 3 | 0
2025-01-24 | Done | Retake | Blcok a | retake | ILO 2.6 | 4 | 4 | 0 |  | I am retaking this block_a since I did not pass it last time
2025-01-24 | Done | task 9 to 15 | Making a read me file | Study | ILO 5.1 | 3 | 3 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 47 | 49.5 | 2.5

## Overview (hidden)
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
If you add more rows to the Worklog Tasks and Time sheet, make sure to update the row count accordingly. For example, if you add an additional row for Week 1, you'll need to adjust all formula in Column C from H14 to H15 and F14 to F15 | bar: W1 to W4

## Drop-downs (hidden)
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 0.3
Unplanned | Meeting | ILO 1.5
Blocked | Programming | ILO 2.5
In-Progress | Research | ILO 3.5
Done | Testing | ILO 4.4
Delayed | Workshop | ILO 7.3
Cancelled | Planning | ILO 11.2
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break